## Week 09
WEEKLY REPORT Week 09 from 02/03 to 06/03/2026
Employee’s name: Vu Minh Hieu Title: AI Intern Unit/Dept: Linagora Vietnam
Your days off this week: |  | Number: 0 Date:
Your working days at the office this week: |  | Number 3 Date: 09 - 10 – 11 - 12 / 03
COMPLETED WORK
NO | PROJECT/TASK | DESCRIPTION OF ACTIVITIES | TIME SPENT | RESULT VS PLAN |  | GAP (if any) |  | REMARK
|  |  |  | Completion (%) | Gap (%) | Reason | Solution/Deadline
1 | Load Qwen 3.5 , 3 model on Kaggle and evaluate | - Check system compatibility, model quantization version - Load Qwen 3.5 9B and 3 8B and run the benchmark | 14HD | 60% | 40% | - Hardware constrain require some compromise on data/model quality to perform benchmark - Time consuming evaluation process - Occasional coding error | Complete benchmark result by the end of | Some quantization still not compatible with the current kaggle hardware
2 | Find new dataset for Qwen | - Check system compatibility, model quantization version - Check dataset info, datatset quality - Dataleakage ??? | 8HD | 100% |  |  |  | https://github.com/VuMinhHieu-20225494/linagora_internship/tree/main/week1
3 | Investigate what benchmark is needed for a LLM | General knowledge, question answering, instruction following, summarization … | 2HD | 100%
4 | How to evaluate LLM on specific capabilities | Metrics for each LLM capability | 2HD | 100%
5 | Self-study | what type of dataset need for a LLM (instruction, conversation, general web text …) | 3HD | 100%
… | Reviews, meetings, support, community, … |  | 1.5HD |  |  |  |  | All the meetings or additional tasks here
No | OBJECTIVE FOR NEXT WEEK |  | Note |  | * The things that went particularly well this week (area of improvement, new task....)
1 | What are you going to do this week.
2 | Finish benchmarking design |  | Complete the remaining two benchamrk, find Vietnamese native model |  | * The things that were challenging this week (issue, problem, difficulty,..)
3 | Checking GPU pricing plan
4 | Ticket OpenRAG |  |  |  | * Your proposal, suggestion, request…
5
| Employee: Vu Minh Hieu |  |  |  |  | Teamleader/Manager: Nguyen Quang Trung